COMMUNITY-BASED FOREST MANAGEMENT PROJECT (CFP)

FIRST QUARTERLY REPORT (Draft)

1 FEBRUARY - 31 MARCH 2014

ZAMBIA

April 2014

This publication was produced for review by the United States Agency for International Development. It was prepared by BioCarbon Partners.

This document was produced for review by the United States Agency for International Development.  It was prepared by BCP for the USAID/Zambia CFP, Agreement No. AID-611-14-000001.

Principal contacts:

Vaneska Litz, Chief of Party, Tetra Tech, Lusaka, Zambia, cop@biocarbonpartners.com

Hassan Sachedina, BioCarbon Partners, Managing Director/Deputy Chief of Party, hassan@biocarbonpartners.com

Implemented by:

BioCarbon Partners

34 Chitimene Road

Lusaka, Zambia

COMMUNITY-BASED FOREST MANAGEMENT PROJECT (CFP)

##### (Draft) First Quarterly Report– February – March 2014

MAY 2014

###### DISCLAIMER

The author’s views expressed in this publication do not necessarily reflect the views of the United States Agency for International Development or the United States Government.

Contents

Acronyms	ii

Introduction	1

Management Activities	2

Cross-Cutting Technical Activities	4

Technical Activities	6

Appendices	12

APPENDIX 1: CFP STAFF LIST as of 4/30/2014	13

APPENDIX 2: LIST OF SUBMITTED DELIVERABLES	14

# Acronyms

AO		Agreement Officer

AOR		Agreement Officer’s Technical Representative

BCP		BioCarbon Partners

CA		Cooperative Agreement

CCBA		Climate Community and Biodiversity Alliance

CFP		Community-based Forest Management Program

COP		Chief of Party

DCOP		Deputy Chief of Party

EA		Environmental Assessment

EMMP		Environmental Management and Mitigation Plan

FAM		Finance and Administration Manager

GRZ		Government of the Republic of Zambia

IEE		Initial Environmental Examination

REDD		Reducing Emissions from Deforestation and Forest Degradation

RFQ		Request for Quotations

SUS		Start-up Specialist

USAID		United States Agency for International Development

USFS		United States Forest Service

VCS		Verified Carbon Standard

# Introduction

USAID has awarded a Cooperative Agreement to BioCarbon Partners, Ltd (BCP) to implement the Community-based Forest Management Program (CFP) in Zambia.  The CFP is the flagship piece of USAID/Zambia’s Global Climate Change project under the Presidential GCC Initiative and is designed to exemplify and support the Government of Zambia’s (GRZ) Reducing Emission from Deforestation and Degradation (REDD+) strategy by establishing the largest REDD+ program to-date in Zambia.

CFP will focus on three major objectives: emissions reductions from deforestation through participatory natural resource management of globally biodiversity significant forested landscapes; poverty reduction through improvements in smallholder farmer agricultural productivity, development of non-timber forest products and expansion of markets and value chains; and support to the GRZ to develop a legal framework and pilot project to demonstrate the viability of REDD+ as a replicable forest management  strategy.

Section A.7(2)f of the Cooperative Agreement between BCP and USAID requires that BCP report to USAID quarterly on the following:

- A comparison of actual accomplishments with the goals and objectives established for the period, the findings of the investigator, or both. Whenever appropriate and the output of programs or projects can be readily quantified, such quantitative data should be related to cost data for computation of unit costs;

- Reasons why established goals were not met, if appropriate;

- Other pertinent information including, when appropriate, analysis and explanation of cost overruns or high unit costs;

- Environmental Monitoring and Compliance updates.

As the report sections that follow reveal, February and March were a period of intense planning and preparation for field activities that will require a massive increase in BCP staff, resources, and capacity to manage this ambitious program. Accordingly, the focus of activities was primarily on recruitment for core administrative and technical staff, development of systems, and procurement of equipment, and selection of a suitable office space.  In addition, the core management team met frequently to discuss reorganization of personnel and programming to ensure that BCP’s core program and CFP are as integrated as possible to reduce replication of efforts and positions within the organization.

As would be expected with this scale of expansion, there have been significant challenges associated with this start-up period. However, as is outlined below, important strides have been made to ensure a solid foundation for CFP implementation.

Organization of the Report

For this first quarterly report, BCP has structured the report around three major sections:  Section 1 covers management activities; Section 2 provides an overview of cross-cutting technical activities; Section 3 provides a narrative description of technical activities matched against activities described in the approved Mobilization Plan.

It is anticipated that future quarterly reports will be organized to align with the Annual Work Plan activities and results framework.

# Management Activities

The vast majority of activities that were undertaken by CFP were related to management and administration and the development of the related systems that will be necessary to support this large project across a wide and varied landscape.  Development and implementation of these systems and related activities has been hampered by delays in funding (USAID’s first advance was not received until the first week of March 2014) and hiring of support staff (funding delays hindered recruitment efforts, and successful applicants required at least 30-days notice before they were able to begin).  More importantly, the introduction of new policies and systems required the COP and DCOP (who is the Managing Director of BCP) to meet, confer and agree on policies not just for the project, but for the organization writ large.  This has been particularly challenging given the different levels of funding that are received across projects within the company.

Staffing:

In response to USAID’s request for a rapid startup, BCP mobilized Finance and Administration Manager (FAM), Moses Masese in the last week of January to initiate activities to jump start the project startup including identification of a suitable office space, drafting scopes of work for administrative positions, developing Requests for Quotations (RFQ) for equipment purchases, opening bank accounts and identifying legal service providers.  Subgrantee, Tetra Tech, mobilized the Chief of Party (COP) on February 5, 2014 and a Start-up Specialist (SUS), Chelsea Keyser on February 9, 2014 to provide additional support to the startup efforts.  Primarily through the efforts of the FAM and SUS and as required in the terms of the Cooperative Agreement (CA) (see Section A.20 Special Award Conditions), a recruitment process was put in place to ensure that recruitment was fair and competitive; a review of the budget was undertaken to determine a viable and sustainable salary scale and compensation package across the organization (inclusive of other BCP activities not funded by USAID).

Advertisements were put in newspapers, on the BCP website and through professional networks for the following positions: Procurement and Logistics; Administrative Assistants; Administration Officers; Finance Officers; M&E Officers; Community Engagement Managers; Forest Governance Lead; GIS Specialist and Forest Management Lead. Following review of applicant CVs, interviews with shortlisted candidates were conducted and continue into the next quarter.  It is anticipated that final candidates for all of these positions will be identified before the end of April (the official Mobilization Period for CFP).

In addition to new staff recruitment, four key technical staff began working on CFP beginning February 1, 2014: Dr. Hassan Sachedina, the Deputy Chief of Party (DCOP); Livelihoods Lead, Ms. Molly Crystal; Dr. Leon Theron (Measuring, Reporting and Verification Lead); and Dr. Wesley Roberts (Geospatial Manager).  It should be noted that Ms. Crystal’s position will be changed to Technical Team Coordinator in response to organizational changes developed through the Annual Work Planning process in March and April 2014.

Following work planning, a reorganization of the project and positions is being proposed and will be finalized during the next quarter and in the first annual Work Plan.  This includes a revision in the lines of reporting, changes in titles, scopes of work, and the creation of shared positions between BCP projects.

Subcontract Administration:

The Tetra Tech subaward was signed in January 2014 and USAID approved pre-startup costs for the mobilization of the COP and her family.  In addition to the COP, Tetra Tech provided technical short term assistance for startup activities through 35 days of LOE from Startup Specialist, Chelsea Keyser; Senior Technical Advisor/Manager, Dr. Matt Sommerville (facilitation of work planning and related startup support); Mr. John Nittler (preparation of a draft EMMP); and Joe LeClair, Senior M&E Associate (preparation of the M&E Plan)

Three of the named staff in the approved CFP budget (Drs. Sachedina, Roberts and Theron) are actually staff of BCP’s parent company, BCP Mauritius (BCP/M).  This was brought to the attention of USAID in February 2014 and the Agreement Officer (AO) has agreed to a subaward to BCP/M for Drs. Roberts and Theron.  It is anticipated that a sub-award to BCP/M will be prepared for USAID approval following these discussion in May 2014.

Offices:

BCP moved from its two-room office in the Musika Compound to an office compound in North Mead, Lusaka.  A one-year lease was signed with the landlord.

Procurement:

Section A.20 of the Cooperative Agreement requires BCP to establish, document and maintain a system for procurement.  Accordingly, a procurement plan was developed and submitted to USAID in February 2014.  USAID has provided feedback on that draft and the systems outlined in the plan have been adopted for procurement by BCP as an organization.

Using these processes, BCP has procured office furniture for the new offices.  In addition, BCP procured electronic payroll software (a Special Provision of the Cooperative Agreement Section A.20) and accounting software and licenses.  Computers and printers were purchased and the new office was wired for intra-office connectivity to the printers and Internet.  Five vehicles (1 Hi-lux, and 4 Land Cruiser models) were procured in late March from Toyota Gibraltar at considerable cost savings compared to local rates for comparable vehicles.  An additional 3 vehicles will be procured in April 2014, and motorcycles will be sourced for procurement in the upcoming months to support site selection and other field activities.  Legal services were also procured in order to review and revise BCP contracts and human resource policies for consistency with Zambian labor law.

Other Management Activities:

In addition to the activities outlined above, BCP also drafted and submitted a Mobilization Plan that was approved by USAID in February 2014.  This document has provided guidance to the BCP team for the mobilization period (February 1-April 30, 2014).  Other relevant activities for the period include:

- Bank Accounts established;

- Chart of Accounts set up and financial systems put in place (CA Section A.20 requirement);

- Development of a Human Resources Policy Manual (CA Section A.20 requirement) that was reviewed by USAID/Zambia’s Executive Officer and AOR; and

- The development of a Branding and Marking Plan that was submitted to USAID in February and approved by USAID in March 2014.

# Cross-Cutting Technical Activities

Performance Monitoring:

The Cooperative Agreement requires that BCP prepare a M&E Plan for CFP by May 1, 2014 (see CA Section A.7(2)e).  This plan will include specific plans to document, monitor and evaluate program performance using quantifiable performance indicators and targets for the overall objectives included in the program description and activities in annual work plans.  This will also include customized indicators that BCP will need to track to attain carbon verification standards.  The plan will describe the data collection and measurement processes.

In a meeting between the Agreement Officer’s Representative (AOR) and Economic Growth Team Leader on February 7, 2014, it was agreed that life of program targets would be finalized with the submission of the FY15 Work Plan that will include an updated M&E plan.  This delay will allow BCP to finalize the sites and develop realistic targets. With assistance from Tetra Tech ARD’s Senior M&E Specialist, Joe LeClair, BCP has prepared a draft M&E Plan that will be finalized in May following input from USAID.

BCP has budgeted for a Senior M&E Officer and two M&E Officers to support M&E efforts on the project.  Recruitment for these positions will continue in the next quarter.  However, applicants for the position have been generally weak.  As a result, BCP is considering the possibility of providing STTA to mentor staff.

Environmental Monitoring and Mitigation Plan:

BCP is required to submit an environmental mitigation and monitoring plan (EMMP) in conjunction with the first annual work plan (see CA Section A.7(2)c).  In March, a Tetra Tech ARD Natural Resource Management expert, John Nittler, prepared a preliminary draft EMMP that built on the CFP Initial Environmental Examination (IEE) and outlined how BCP would implement the conditions of the IEE in order to mitigate and monitor environmental impacts.

The IIE did identify some Positive Determinations (of environmental impact) emanating from the proposed eco-charcoal production and wildlife-based consumption activities, such as game ranching or game hunting, and indicated that a Positive Determination in future may be found for certain NTFP.  Accordingly, an independent Environmental Assessment (EA) addressing the environmental concerns raised by these activities will be conducted in Year 1 or once the sites selection process narrows down the target areas for CFP activities.  Based on these findings the EMMP will be revised and integrated into the Work Plan.  BCP understands that these Positive Determination activities cannot proceed until the EA has been conducted and the EMMP revised in order to minimize adverse impacts on the environment.

The draft EMMP will be submitted to USAID for approval in May 2014.

Work Planning:

The core CFP technical team, including the COP, DCOP, Technical Team Coordinator, Carbon Accounting Manager and Geospatial Specialist spent three days in work planning sessions facilitated by Tetra Tech STAM, Dr. Matt Sommerville.  Outputs from the sessions are being used to draft the FY14 work plan.

Staff Development:

Financial and human resource management policies and systems have been put in place during the period in compliance with special provisions required by the CA (see Section A.20).  As part of the Startup Activities, the SUS developed several presentations that will be used to orient BCP staff (both current and future employees) on the implementation of these systems.

# Technical Activities

Key Accomplishments and challenges:

As mentioned above, the vast majority of activities have focused on the development of systems, recruitment of staff and other administrative and management tasks.  In addition to these, CFP technical staff has begun to several technical activities as identified in the initial mobilization plan. Key technical results achieved are listed in tables below, and are then described in greater detail in the sub-sections to follow.

RESULTS FOR FY14 Q2

ACTIVITY 1: Project Area Site Selection

1.1 Geospatial analysis of deforestation threats in potential CFP target areas initiated

1.2 Site-Selection Tool (comprehensive spreadsheet tool) developed

1.2 Viability screening of sites initiated

1.3 Consultations initiated with Districts, Traditional Authorities, communities, FD, CRB and ZAWA

1.6 Initiated process of acquiring USFS land cover data set to complete land cover classification of target PFMAs

1.8 Preparation of training schedule, plan and materials for training PRA methodologies initiated

1.1 Refine geospatial analysis of deforestation threats in potential CFP target areas

BCP analyses deforestation threats using a site selection tool that analyses three main sets of data: topography (“digital elevation model”), tree cover and carbon density. In this first quarter of start-up implementation, BCP’s Geospatial Manager developed an initial “pixel based” site suitability index, as well as a more detailed “polygon based” site selection tool to identify deforestation threats in potential CFP target areas.  The results of these initial deforestation analyses will be further refined in upcoming months through expert opinion and on-the-ground assessment of other criteria as part of the more detailed site selection process.

Topography: The topography data set has been created using slope and elevation data. This tool is able to provide an approximate model of deforestation from subsistence agriculture, which is generally practiced on slopes less than 20o.

Tree cover: Forest cover is a key component variable in the site selection process. BCP’s Geospatial and Carbon Accounting Team has used the Hansen Global forest change data set, which contains the most recent assessment of forest cover in the provinces of interest to determine forest cover in 2012. The forest cover data will help to select a site that has sufficient biomass to warrant the establishment of a large scale REDD+ project.

Carbon Content: To determine the spatial distribution of forest biomass carbon and the total carbon stored in the forest (above and below ground), BCP employed the Saatchi et al (2011) map of both above and below ground Carbon content. This map is based on a combination of millions of forest height data derived from the ICESAT GLAS Lidar, landscape characteristics from optical and radar satellite imagery, and forest plots distributed over the region, and is thus considered to be very comprehensive.

1.2 Begin viability screening of sites

BCP has developed a comprehensive site selection spreadsheet tool that scores sites based on criteria informed by international carbon standards, specifically the Verified Carbon Standard (VCS) and Climate Community and Biodiversity Alliance (CCBA) Standard, as well as experiences from REDD project implementation.

Each criterion has been weighted and a score assigned based on geospatial analysis, expert opinion or peer reviewed publications. If certain criteria are not met the tool generates the result “Failed” and it means the project does not meet certain critical criteria to be suitable as a REDD project.

One of the most important criteria for site selection is the presence of a clear deforestation threat to potential sites, e.g. if a site is too mountainous to be cultivated it most likely is not a suitable REDD site, unless there is potential logging of high value timber species.

Land tenure and rights holder consent are also important criteria, which will be evaluated through consultations with local stakeholders and experts. At this phase of REDD project implementation it is important to identify any early indications of land rights or boundary disputes, as these will need to be treated with circumspect.

The tool scores each site as a fraction of one, the higher the score the more suitable a site will be.

1.3 Begin consultations with Districts, Traditional Authorities, communities, FD, CRB and ZAWA

Meetings with the Ministry of Lands, ZAWA and the Forestry Department were initiated in the reporting period and will be held in the upcoming months.

1.6 Complete land cover classification of target PFMA

Comprehensive land cover classification will begin once the project sites are identified. In the interim, BCP will make use of a land cover data set produced by the United States Forest Service's (USFS) to assist in a preliminary assessment of land cover classification.  This information will be validated during the site selection process later in the year.

1.8 Prepare for training in PRA methodologies

Staff training for new BCP-CFP staff members is planned to take place in June 2014. In April, BCP’s Technical and Management teams began preparing training materials, including the preparation of training materials and development of a training program for PRA methodologies.

1.11 Begin development of cumulative deforestation model

Once the site selection has been completed, BCP will select a suitable reference area where a cumulative deforestation model (CDM) will be built.  BCP’s Carbon Accounting Manager and Geospatial Specialist are currently researching options and alternative models to ensure that the CDM will adhere to the strict guidelines stipulated by leading compliance methodologies.

RESULTS FOR FY14 Q2

ACTIVITY 2: Stakeholder Engagement

2.3 Preparation for village-based FPIC consultations: new staff training, consultation plan and materials developed

2.5 REDD+ banner templates and comics developed, along with other consultation/publicity materials

2.6/4.15 Social monitoring applications identified, pilot survey / databases developed; plan in place for equipment procurement

2.15 Initial outreach to local government

2.3 Prepare for village-based FPIC consultations

During the intensive work planning program that took place in March 2014, BCP’s key technical team was able to identify a timeline for site-selection/viability assessment activities that will begin in July 2014 following the completion of an initial “desk review” viability assessment process.  This process will be outlined in detail in the Annual Work Plan.

2.5 Develop REDD+ banners and comics in Nyanja and other local languages

Banner templates, comics, and basic sensitization materials (brochures) have been developed under BCP’s pilot project.  Translations into specific languages will be determined once a schedule for site selection is finalized in May 2014.  Additional materials will be created as needed, based on experiences and feedback once on-the-ground consultations begin.

2.6 & 4.15: Design data capture applications for social monitoring

BCP has piloted the use of social monitoring surveys through the Community Engagement Team activities connected to the Lower Zambezi REDD+ Project pilot. These same surveys, and survey designs, will be used and used as templates/foundations for the development of additional surveys in the context of the CFP. Next steps include the procurement of android phones and the hiring of an IT specialist or equivalent professional, along with hiring key staff for the M&E Team, who will develop a robust database for data management and provide training to relevant personnel.

2.9 Initiate relations with regional radio stations for future programming

This activity has been postponed until a site selection schedule is finalized (anticipated in May 2014).

2.14 Collect local census data

This activity has been postponed until a site selection schedule is finalized (anticipated in May 2014).

2.15 Preliminary outreach to local government

During the period, discussions were initiated between BCP and the Rufunsa District Commissioner, along with Senior Chief Luembe in Nyimba District to discuss the possibility of expanding CFP activities into these areas.

RESULTS FOR FY14 Q2

ACTIVITY 4: Verification

2.6/4.15 Social monitoring applications identified, pilot survey / databases developed; plan in place for equipment procurement

4.17 Committee for IT System Development established, comprised of TTC, GIS Manager and Carbon Accounting Manager

4.15 & 2.6: Design data capture applications for social monitoring

See 2.6 above

4.17 IT data storage and filing system developed

BCP has set up a committee comprised of the Technical Team Coordinator, Geospatial Manager and Carbon Accounting Manager to identify and develop the most appropriate data management, storage, filing and communications system for BCP’s rapidly expanding staff. Currently, Gdrive communications and data/file management systems have been developed and are in place, and an ODK-based data collection system is linked to a simplified Excel management system, that is currently stored within the same Gdrive system, for the purposes of biomass and social data collection. These systems will be developed throughout May 2014, introduced to staff during training sessions in June 2014, and further developed as the program expands.

RESULTS FOR FY14 Q2

ACTIVITY 6: Policy and Governance Framework

Support provided to GRZ to develop a Concept Note for potential REDD+ activities

Discrete tasks under this Activity were limited during the period to discussions between the Forestry Department and USAID on the content and development of a concept note for GRZ submission to the World bank in consideration of funding for Piloting Jurisdictional REDD+ in the Luangwa Valley through the Biocarbon Fund Initiative for Sustainable Forest Landscapes.  It is anticipated that development and submission of this Concept Note will be finalized in the next quarter.  A successful application will provide additional funding and support for REDD+ activities in Zambia, but will likely require a jurisdictional app

RESULTS FOR FY14 Q2

ACTIVITY 7: Improving Sustainable Livelihoods and Generating/Sharing Revenue

7.1.1/7.2.5/7.8.1 Consultations and partnership-seeking discussions with USG-funded agencies in target areas initiated

7.2.1 Small enterprise management documents developed

7.4.4 Possible viable partners and NTFP co-investors identified

7.1.1/7.2.5/7.8.1: Consultations and partnership seeking with USG-funded agencies in target areas

Initial consultations to introduce the program with FZS and ASNAPP and will continue throughout the upcoming months.

7.2.1: Develop Small Enterprise Management Development Strategy

Because livelihoods interventions are not anticipated to begin until early 2015, the completion of this strategy document has been postponed.

7.4.4 Seek viable partners and NTFP co-investment

This activity will begin in the next quarter.

# Appendices

## APPENDIX 1: CFP STAFF LIST as of 4/30/2014

Full-time Staff: Lusaka

|  | Last Name | First Name | Function | Subcontract Organization | Start Date |
| --- | --- | --- | --- | --- | --- |
| Technical |  |  |  |  |  |
| 1 | LITZ | Vaneska | Chief of Party | Tetra Tech | Feb. 7, 2014 |
| 2 | SACHEDINA | Hassan | BCP Managing Director and Deputy Chief of Party | BCP | Feb.1, 2014 |
| 3 | THERON | Leon | Carbon Accounting Manager | BCP/M | Feb 1, 2014 |
| 4 | ROBERTS | Wesley | Geospatial Specialist | BCP/M | Feb 1, 2014 |
| 5 | CRYSTAL | Molly | Technical Team Coordinator | BCP | Feb 1, 2014 |
| Financial and Administrative |  |  |  |  |  |
| 6 | MASESE | Moses | Finance and Administration Manager | BCP | Feb 1, 2014 |
| 7 | SAMPA | Clara | Procurement and Logisitics Officer (P/T) | BCP |  |
| 8 | CHANDA | Bwalya | Administrative Assistant (P/T) | BCP |  |
| Support Staff |  |  |  |  |  |
| 9 | THEO | Lackson | Driver | BCP | Feb 1, 2014 |

## APPENDIX 2: LIST OF SUBMITTED DELIVERABLES

|  | Title | Date Submitted | Reference (Deliverable/Reporting Requirement) | Notes |
| --- | --- | --- | --- | --- |
| 1 | 3-Month Mobilization Plan | Feb. 18, 2014 | A.7.2a | Approved Feb. 24, 2014 |
| 2 | Branding and Marking Plan | Feb. 18, 2014 | A.7.2d & M9 | Approved March 26, 2014 |
| 3 | Procurement Plan | March 4, 2014 | A.20.1 | Received feedback from AO on 3/17/14 |
| 4 | Human Resources & Travel Policies | March 17, 2014 | A.20.IV | Comments received from USAID/Zambia Executive Officer on March 21, 2014 |

U.S. Agency for International Development

Zambia Mission

Ibex Hill

Lusaka, Zambia

Un index pour évaluer le renforcement des capacités des autorités municipales (cadre exécutif/administratif) (Résultat 2); (2) un système similaire pour évaluer les capacités des assemblées ; et (3) une base de données municipale pour suivre les progrès municipaux dans la gestion de fourniture de services, la transparence et la gestion financière