Thank you again for meeting with us this week. Please see the attached Feasibility Assessment that informed the design of our end line evaluation for Zambia CFP, as requested.

We also have the following questions regarding BCP’s implementation in response to the spreadsheet shared with us on Monday:

- According to the excel file provided, there were no interventions in Msoro (initially a treatment area) or Masemphangwe (initially a control area) chiefdoms. We wanted to confirm that this was the case, and see if BCP is able to share any information about why treatment might not have happened in Msoro as initially planned.

  - Similarly, for Nyalungwe and Mwanya chiefdoms (initially control areas), the excel file provides information on interventions they received. We wanted to see if BCP is able to share any information about why treatment was expanded to these areas, as it was not initially planned.

Response: Based on the engagements conducted at the time, Nyalungwe and Mwanya were always part of the project areas planned for interventions. The project was meant to create a continuous corridor for wildlife movement connecting the North Luangwa, South Luangwa National parks to Lower Zambezi National and to the Mana pools in Zimbabwe as well as the Nyika National Park in Tanzania and Kasungu National Park in Malawi through the Mozambique Tanzania Transfrontier Conservation Area (MZTFCA). The scope of planned engagements did not include Mwasephangwe, and neither was it mentioned in the PD.

Interventions were done in Msoro; Maize shellers were procured and delivered for use by the farming communities of Msoro. These were managed by the respective Village Action Groups from the Community Resources Board. In addition, a Mothers shelter (remote outreach station for Under 5 immunization and Antenatal Care) was under construction in Msoro. However, this was never handed over as MOH requirements for a functional station were not met; Station required access to Clean Water Supply. There was shift and focus towards implementation of livelihood projects at household level.

All intervention information provided in the excel file seems to be at the chiefdom/CRB level (i.e., it is the same for all villages in a chiefdom), rather than at lower levels of the VAGs or villages. However, based on the notes, it seems like some interventions did indeed take place in more specific, smaller geographic locations. For example, in Luembe chiefdom, the interventions include: “Construction of teachers houses in Chinambi, Ngambwa, Ambo, Mushalila & Rehab at Chikwasha & Rehabiliation of 1*2 Classroom block, Mbilisao”. Can more information be provided about these locations? Are these village names, or something else? Same question applies throughout the rest of the interventions listed.

Response (see additions in red)

| CFP USAID Project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Period: 2014 - 2019 |  |  |  |  |  |
|  | Sector | Chiefdom | Project | Year | Comments |
| 1 | Nyimba | Luembe | Hammermill | 2017 | Large majority of Livelihoods and Community projects in this area was implemented from 2021 (post USAID project) |
|  |  |  | Procurement of a fibre glass boat for communities from Malopa VAG to be stationed at Malope Village and used for crossing at the Lusemfwa River Crossing Point | 2017 | Still in use |
|  |  |  | Construction of one Teachers house at Chinambi primary school located in Chinambi VAG | 2017 | Completed and handed over |
|  |  |  | Construction of one Teachers house at Ngambwa Primary School in Ng'ambwa VAG | 2017 | Completed and handed over |
|  |  |  | Construction of teachers house at Simalama Primary School in Simalama VAG | 2017 | Completed and handed over |
|  |  |  | Construction of teachers house at Ambo Basic School in Chalubilo VAG | 2017 | Completed and handed over |
|  |  |  | Construction of two teachers' houses at Mushalila Primary School in Chisanga VAG | 2018 | Completed and handed over |
|  |  |  | Rehabilitation of one Teachers house at Chikwasha Primary in Chikwasha VAG | 2019 | Completed and handed over |
|  |  |  | Rehabilitation of 1x2 classroom block at Mbilisao Primary School in Mbilisao VAG | 2019 | Completed and handed over |
|  |  | Nyalugwe | Construction of 1 by 2 classroom block at Mkoma Primary in Mkoma VAG | 2017 | Completed and handed over |
|  |  |  | Construction of a staff house for a teacher at Mvuwa Primary School in Mvuwa VAG | 2017 | Completed and handed over |
|  |  |  | Procurement of a fibre glass boat for use by the community of Kasansamula village in Kasansamula VAG | 2019 | Still in use, biut in bad shape |
|  |  |  | Construction of staff house for a teacher at Mkoma Primary school in Mkoma VAG | 2019 | Completed and handed over |
| 2 | Mfuwe | Msoro | Procurement and delivery of three Maize Shellers to be managed by Msoro CRB to support farming communities in Kasamanda, Kawala and Nyakatokoli VAGs | 2017 | Large majority of Livelihoods and Community projects in this area was implemented from 2021 (post USAID project) |
|  |  |  | Construction of Under 5 immunization center/ Antenatal Outreach station in Pende VAG | 2017 | The center is not functional as it needs to meet the MoH Standards as well as awaiting for water installation. There has also been a shift of priority to livelihood programs to directly benefit households. |
|  |  | Malama | Moulding of 9000 bricks for construction of Chilongozi Secondary school in Malama VAG | 2017 | Blocks were moulded by community, were used to construct a dormitary at Chilongozi School (the one next to the palace) |
|  |  |  | Repair of roof to teachers house at Chilongozi Primary School in Malama VAG | 2018 | completed |
|  |  |  | Repair and replacement of broken window panes to head teachers house at Chilongozi Primary School in Malama VAG | 2018 | completed |
| 3 | Lundazi | Mwanya | Procurement and supply of Clinic Furniture at yakobe clinic in Yakobe VAG | 2016 | Delivered but not in use, as clinic which was built under CDF was demolished, but the Furniture is available awaiting for new clinic to be commissioned through CDF (Furniture is being kept at Yakobe Primary School) |
|  |  |  | Procurement of fibre glass Boat to be stationed at Lukusuzi River Crossing point in Mkwela VAG | 2016 | Delivered but not currently in use coomunity using a bigger boat supplied under Disaster Management & Mitigation unit (DMMU) - (Mwasewaminga Community Boat) Note: this is the only corssing point from Lundazi Lumezi town into the Chiefdom |
|  |  |  | Construction of Teacher's House at Mkasanga Basic School in Mkasanga VAG | 2017 | Substandard, not in use |
|  |  |  | Construction of Teacher's House at Mwanya Basic School in Mkwela VAG | 2017 | Substandard, not in use |
|  |  |  | Construction of Teacher's House at Lukusuzi Community School in Lukusuzi VAG | 2017 | Substandard, not in use |
|  |  |  | Construction of Clinic Staff House at Yakobe Clinic in Yakobe VAG | 2017 | Substandard, not in use |
|  |  |  | Solar electrification of Classroom at Mkasanga Basic School in Mkasanaga VAG | 2018 | Delivered and installed |
|  |  |  | Solar electrification of Mkasanga Rural Health Post in Mkasanga VAG | 2018 | Delivered and Installed |
|  |  | Masemphangwe | N/A |  |  |

- All the information provided seems to be for projects implemented from conservation funds. Are you able to share implementation details regarding any other activities: livelihood improvement activities, training and capacity building, other disbursements of conservations funds?

@ Mike Besides the apiculture activities implemented through Beesweet all other livelihood interventions implemented are post USAID funding.

Worth noting that Beesweet failed to perform as expected and the relationship was terminated. Minimal training support was provided to Lead Farmers in Rufunsa on the Conservation Farming Min-Till activities and limited training was provided through the DACO’s office in Mfuwe to farmers.  The ramping up of these activities has been post-USAID.

We understand that implementation ended quite a while ago, before you joined BCP, and that there are limited personnel and project documents remaining from that time, so you may not be able to answer all our questions. Any insight you and your team could provide is greatly appreciated, and we’re happy to set up a call again sometime in January to discuss.